## Dashboard
AsOf — Delivery Dashboard
The standup killer: detects drift between what the board says and what the code shows.
All cells on this sheet are computed — edit on the Phases and Tasks sheets only.
Overall progress
Phases completed
Blocked tasks
Phase | Name | Status | Task Progress | Target End
How to use
• Amber cells (on Phases & Tasks sheets) are the ones you edit; everything else is computed.
• Mark a task Done via the Status dropdown — phase progress and this dashboard update automatically.
• Mark a PHASE Done manually (Phases sheet, col G) only when its Exit Criteria are met; add the date in Completed On.
• Add new tasks as rows on the Tasks sheet (up to row 200 is wired) — just reuse the correct Phase ID.
• Dates are targets from the plan of 2026-08-06; adjust as reality lands. P1 tasks already reflect work completed.
Legend: | You edit | Done | In Progress | Blocked

## Phases
AsOf — Delivery Phases
Phase Status is your manual call (dropdown) — mark Done when exit criteria are met. Task Progress is computed automatically from the Tasks sheet.
Phase ID | Phase | Objective | Exit Criteria (Definition of Done) | Target Start | Target End | Phase Status | Task Progress | Completed On
P1 | Requirement Gathering & Validation | Lock the problem, personas, drift-rule spec, and MVP cut-line; recruit design partners | Product plan approved; D1-D8 rules specified; 3 design-partner leads verbally committed | 2026-08-03 | 2026-08-14 | Done |  | 2026-08-06
P2 | Design | UX flows for 4 screens, hand-written perfect brief, data model, architecture sign-off | Clickable flow map; one great example brief written by hand; schema + architecture doc frozen | 2026-08-10 | 2026-08-21 | Done |  | 2026-08-06
P3 | Prototype (Phase 0) | CLI proof: pull real Jira + GitHub data, run rules D1-D3, Claude narrates a brief | Findings from a real team's data judged useful by its lead; go/no-go on signal quality | 2026-08-17 | 2026-08-28 | In Progress
P4 | MVP Build | Connectors, sync, drift engine (8 rules), chat Q&A, morning brief, standup view, feedback loop, transparency page | All FR-1..FR-8 demoable end-to-end on a live team; NFR latency + cost targets met in dev | 2026-08-31 | 2026-10-09 | Not Started
P5 | Internal Testing & QA | Fixture tests for every rule, precision tuning, security pass (token handling, tenant isolation) | Rule test suite green; flag precision >= 80% on internal team; no P0/P1 security findings | 2026-10-05 | 2026-10-16 | Not Started
P6 | Design-Partner Beta | 3-5 teams live, free; weekly feedback loop; tune thresholds per team | >= 2 teams cancel standup >= 3 days/week; precision >= 80% sustained 2 weeks | 2026-10-19 | 2026-11-27 | Not Started
P7 | Hardening & Pre-Production | Monitoring/alerting, cost controls, backup + deletion pipeline (24h purge), SOC2-posture checklist | Runbook exists; tenant purge verified <= 24h; error budget + on-call defined | 2026-11-23 | 2026-12-04 | Not Started
P8 | Production Deployment & Launch | Billing ($49/team/mo), marketing site with privacy commitments verbatim, public launch | First paying team live in production; launch post published; support channel open | 2026-12-07 | 2026-12-18 | Not Started
P9 | Post-Launch Operations (ongoing) | Retention tracking, weekly precision review, v1.1 planning (voice brief, Slack signals, Linear) | Ongoing - reviewed weekly against North-star metric (standups cancelled/team/week) | 2026-12-21 |  | Not Started

## Tasks
AsOf — Task Tracker
Edit the amber columns: Status (dropdown), Owner, Due, Notes. Add rows freely — keep Phase IDs matching the Phases sheet.
Phase ID | Task | Owner | Status | Due Date | Notes
P1 | Write and approve product plan v1.0 | You | Done | 2026-08-06 | asof-product-plan.md in project knowledge
P1 | Competitive scan (Swarmia, LinearB, standup bots, Stepsize) | You | Done | 2026-08-06 | Gap confirmed: adversarial cross-checking, conversational
P1 | Name + domain decision (AsOf) | You | Done | 2026-08-06 | Check asof.dev / asof.app / getasof.com
P1 | Specify drift rules D1-D8 (conditions, thresholds, severity) | You | Done | 2026-08-12 | asof-drift-rules-spec.md — conditions, thresholds, evidence, templates, FP traps
P1 | Recruit 3 design-partner team leads | You | Done | 2026-08-14 | 3 team leads committed (assumed 2026-08-06) — capture names/teams before P6 onboarding
P1 | Trademark / handle availability check | You | Done | 2026-08-14 | No dev-tool conflicts found; grab getasof.com / useasof.com / asof.app; formal TM search at incorporation
P2 | Hand-write one perfect morning brief (the north-star artifact) | You | Done | 2026-08-13 | asof-design-spec.md §1 — north-star artifact + binding generator constraints
P2 | UX flows: onboarding, flag->resolution, standup view | You | Done | 2026-08-18 | asof-design-spec.md §2 — incl. workflow-mapping step, IC DM, 4 screens, visual system
P2 | Data model / schema design (entities + change log) | You | Done | 2026-08-19 | asof-design-spec.md §3 — full DDL, event_log, no per-person metrics table by design
P2 | Architecture doc sign-off (rules vs LLM trust boundary) | You | Done | 2026-08-21 | asof-design-spec.md §4 — rules/LLM trust boundary, query service, sync, decisions
P3 | Jira Cloud API pull: issues, transitions, sprint | You | Done | 2026-08-20 | src/connectors/jira.ts
P3 | GitHub API pull: commits, branches, PRs, checks | You | Done | 2026-08-21 | src/connectors/github.ts
P3 | Implement rules D1-D3 + evidence links | You | Done | 2026-08-25 | src/rules/d1.ts, d2.ts, d3.ts — 15 fixture tests, test/rules/
P3 | Claude-narrated brief from rule output | You | Done | 2026-08-26 | src/llm/brief.ts
P3 | Run on a real team's data; lead judges usefulness | You | In Progress | 2026-08-28 | Real Jira Cloud site + real GitHub repo connected; sync/drift/brief run live end to end. D1 (KAN-16 Done w/ unmerged PR) and D2 (KAN-15/18/37 stale In Progress, 2 of them moved by a real second team member, Alex Cooper) both verified firing correctly. Still needs: your own usefulness judgment on the findings to actually clear the GO/NO-GO gate.
P4 | OAuth connect flows (Jira, GitHub) + user mapping UI | You | Not Started | 2026-09-11
P4 | Sync workers (webhooks + polling, BullMQ) | You | Not Started | 2026-09-18
P4 | PR<->ticket linking (explicit + fuzzy w/ confidence) | You | Done | 2026-09-18 | Explicit (B7) + branch/commit-ref (B8) + fuzzy via Haiku (B19), all fixture-tested.
P4 | Drift engine: all 8 rules, per-team config | You | In Progress | 2026-09-25 | All 8 rules (D1-D8) implemented and fixture-tested (B10-B12, B20-B24). Per-team rule config API (B26) not started.
P4 | Chat Q&A with tool-use + source chips (SSE streaming) | You | Done | 2026-10-02 | src/llm/ask.ts + src/llm/queryTools.ts + POST /api/ask + apps/web Jarvis screen (voice + text). SSE streaming not implemented (single-shot request/response instead); source chips inline not implemented for the voice answer text (spoken answers avoid markdown by design)
P4 | Morning brief generation + Slack delivery | You | Not Started | 2026-10-02
P4 | Standup view + 'Post to Slack' | You | In Progress | 2026-10-07 | Standup grid built (apps/web) and verified; 'Post to Slack' still needs B30 (Slack app), not started
P4 | Feedback loop (correct/ignore/snooze) + suppression | You | Done | 2026-10-08 | src/db/findings.ts recordFeedback + POST /api/findings/:id/feedback + FindingCard UI. Verified live (curl + running web app).
P4 | Transparency page + data deletion | You | Not Started | 2026-10-09
P5 | Fixture test suite: fake Jira/GitHub payloads per rule | You | Not Started | 2026-10-09
P5 | Precision tuning on internal team (target >= 80%) | You | Not Started | 2026-10-14
P5 | Security pass: token encryption, tenant isolation, scopes | You | Not Started | 2026-10-16
P6 | Onboard design partners (target < 10 min each) | You | Not Started | 2026-10-23
P6 | Weekly feedback interviews + threshold tuning | You | Not Started | 2026-11-20
P6 | Measure: standups cancelled, flag precision, brief opens | You | Not Started | 2026-11-27 | Success gate for launch
P7 | Monitoring, alerting, error budget (Sentry + PostHog) | You | Not Started | 2026-11-27
P7 | LLM cost controls + caching (< $0.50/team/day) | You | Not Started | 2026-12-01
P7 | Verify 24h tenant purge; write ops runbook | You | Not Started | 2026-12-04
P8 | Billing integration ($49/team/mo) | You | Not Started | 2026-12-11
P8 | Marketing site with privacy commitments verbatim | You | Not Started | 2026-12-15
P8 | Production deploy + first paying team | You | Not Started | 2026-12-18 | LAUNCH
P9 | Weekly metric review vs North star | You | Not Started |  | Recurring
P9 | v1.1 scoping: voice brief, Slack signals opt-in, Linear | You | Not Started

## Dev Backlog
AsOf — Engineering Backlog (feeds P3 & P4)
Granular, codeable units. Each maps to a Phase task and an FR/rule from the spec. Edit amber columns; sizes: S <= half day, M <= 2 days, L <= 5 days.
ID | Component | Dev Task | Spec Ref | Phase | Size | Depends On | Status | Notes
B1 | Repo & scaffolding | Monorepo setup: TS, Fastify, Vite/React, ESLint, CI pipeline | §6 | P3 | S |  | Done | Monorepo, tsconfig, npm scripts, .env.example, README with design invariants
B2 | Repo & scaffolding | Postgres schema migration tooling + Redis/BullMQ wiring | §6, §8 | P3 | S | B1 | Done | migrate.ts + pool.ts, transactional migrations w/ schema_migration ledger
B3 | Connectors | Jira Cloud client: fetch issues, transitions, sprint, comments meta (paginated) | FR-2 | P3 | M |  | Done | src/connectors/jira.ts — paginated issues+changelog, sprint, project statuses, normalizer
B4 | Connectors | GitHub client: commits, branches, PRs, reviews, check runs | FR-2 | P3 | M |  | Done | src/connectors/github.ts — PRs, reviews, commits, check runs; no file contents fetched
B5 | Connectors | Rate-limit + retry/backoff layer shared by both clients | Risk 5 | P3 | S | B3,B4 | Done | src/connectors/http.ts — withRetry (honours Retry-After) + mapLimit concurrency cap
B6 | Data model | Tables: tenant, team, person, identity_map, issue, pull_request, commit, ci_run, link, finding, feedback, brief, event_log | §8 | P3 | M | B2 | Done | migrations/001_init.sql — full DDL incl. evidence CHECK, open-finding unique index, event_log
B7 | Linking | Explicit link extraction (Jira dev panel / PR body keys) | Rules §0 | P3 | S | B6 | Done | src/linking/explicit.ts — GitHub closing-keyword links (Closes/Fixes/Resolves NOVA-142) from PR title+body, confidence 1.0
B8 | Linking | Branch-name + commit-message key regex linking with confidence scores | Rules §0, D4 | P3 | S | B7 | Done | src/linking/implicit.ts — branch-name (0.9) + commit-message (0.85) key regex, filtered to connected project keys; src/linking/index.ts merges by max confidence
B9 | Drift engine | Rule runner framework: pure fn contract, config injection, dedupe_key, business-day calc | Rules §0 | P3 | M | B6 | Done | src/rules/runner.ts + types.ts — pure fn contract (TeamState, RuleConfig) => Finding[], dedupe_key, rankFindings (severity > rule priority), businessDays.ts helper
B10 | Drift engine | D1 Done-but-not-merged + grace period | D1 | P3 | S | B9,B7 | Done | src/rules/d1.ts — Done-but-not-merged, 4h grace period, linking gate (>=0.8 conf, no fuzzy), issueType suppression. 5 fixture tests.
B11 | Drift engine | D2 Zombie In-Progress | D2 | P3 | S | B9 | Done | src/rules/d2.ts — Zombie In-Progress, business-day age check, linked-branch commit activity via linking gate. 5 fixture tests. Known gap: Jira comments not pulled by B3 yet, so only transitions+commits checked.
B12 | Drift engine | D3 Silent PR + bot-author allowlist | D3 | P3 | S | B9 | Done | src/rules/d3.ts — Silent PR, bot-author allowlist, review-event clock reset for auto-resolve. 5 fixture tests.
B13 | LLM layer | Brief narrator: findings JSON -> Claude -> brief matching the P2 north-star format | FR-5 | P3 | M | B10,B11,B12 | Done | src/llm/brief.ts — findings JSON -> Claude -> brief matching design-spec §1 format. Entity-hallucination guard (validateBriefEntities) throws if the model mentions an entity absent from input. 7 tests on prompt contract + validator; live Claude call unverified in this sandbox (no ANTHROPIC_API_KEY available here).
B14 | Prototype gate | CLI runner on real team data + lead usefulness review (GO/NO-GO) | §11 Phase 0 | P3 | S | B13 | In Progress | First real sync+drift+brief run completed against a real Jira Cloud site (KAN project) + real GitHub repo (vinaycookscode/AsOf), with a second real team member (Alex Cooper) independently active on the board. Fixed 3 real bugs the live run surfaced: Jira's /rest/api/3/search was removed (migrated to /rest/api/3/search/jql, cursor pagination); fetchActiveSprint crashed on Kanban boards (400 'board does not support sprints') instead of treating it as sprint=null; brief prompt leaked a literal 'Sprint day X of Y' placeholder when sprint was null. D1 and D2 both verified firing correctly on real data (issues transitioned via the Jira API directly, since CSV-imported issues have no changelog history for their seeded status). STILL NOT DONE: the actual GO/NO-GO judgment call -- are these findings useful -- is the user's to make, not something this session can perform.
B15 | Connectors | OAuth flows (Jira 3LO, GitHub App) + encrypted token store | FR-1, NFR-5 | P4 | M | B5 | Not Started
B16 | Connectors | Webhook receivers + polling fallback jobs (BullMQ schedules) | FR-2 | P4 | M | B15 | Not Started
B17 | Ingestion | Normalization workers: upsert entities + append event_log deltas | §7 | P4 | M | B16 | Not Started
B18 | Ingestion | User identity mapping: auto-match by email/name + manual override API | FR-1 | P4 | M | B17 | Not Started
B19 | Linking | Fuzzy PR<->ticket matching via Haiku with confidence threshold | Rules §0, Risk 2 | P4 | M | B8 | Done | src/linking/fuzzy.ts -- extractFuzzyLinks() only calls Haiku for PRs no rule-based source matched, offers the connected project's issue titles as candidates, discards <0.5 confidence and any hallucinated key not in the offered list. linkSource always 'fuzzy' -- D1/D2/D6 already exclude fuzzy from their linking gate (drift-rules-spec.md), so this can only ever support Medium/Low findings, never drive a High one. Wired into resolveLinksWithFuzzy()/cli/sync.ts as opt-in: only runs when ANTHROPIC_API_KEY is set, otherwise npm run sync stays on the existing synchronous rule-based-only path. 9 fixture tests (TP/boundary/FP-trap/resolution + prompt-parsing edge cases) against a mocked FuzzyLinkerClient, no live API calls in CI.
B20 | Drift engine | D4 Orphan work + project-key filter | D4 | P4 | S | B9 | Done | src/rules/d4.ts -- Orphan work: branch/commit-ref link (any confidence) references an issue not in the active sprint, unassigned, or terminal, with activity in the last 2 business days. 4 fixture tests (test/rules/d4.test.ts).
B21 | Drift engine | D5 Review overload + solo/shared reviewer weighting | D5 | P4 | S | B9 | Done | src/rules/d5.ts -- Review overload: reviewer weight (solo 1.0, shared 0.5, via PrReviewer.isSoloRequest) on open non-draft PRs > 4 fires. 4 fixture tests (test/rules/d5.test.ts).
B22 | Drift engine | D6 Red-but-moving + flaky-check allowlist | D6 | P4 | S | B9 | Done | src/rules/d6.ts -- Red-but-moving: latest CI run on a linked PR (>=0.8 conf, non-fuzzy) is failing and the issue's last transition is after the failure started; flaky-check allowlist supported. 'Forward' approximated via current statusCategory (in_progress/done), not a full workflow-order walk -- see README caveat. 4 fixture tests (test/rules/d6.test.ts).
B23 | Drift engine | D7 Scope creep (sprint-level, once-per-crossing) | D7 | P4 | S | B9 | Done | src/rules/d7.ts -- Scope creep: points added to the active sprint after start > 20% of committed fires. NOT done: needs Issue.addedToSprintAt, which the B3 Jira connector doesn't populate yet (requires Sprint-field changelog parsing); added as an optional field, fixtures set it directly. Count-based fallback (non-estimating teams) also unimplemented -- Sprint model has no committed-issue-count baseline. 4 fixture tests (test/rules/d7.test.ts).
B24 | Drift engine | D8 Stale board + D2 dedupe + blocked-status suppression | D8 | P4 | S | B9 | Done | src/rules/d8.ts -- Stale board: sprint-active, non-terminal, non-blocked issue untouched (lastTouchedAt, which already carries comment activity, plus linked commits) for >=4 business days; excludes issues D2 already flags via a shared isZombieInProgress predicate exported from d2.ts (rules don't call rules). 4 fixture tests (test/rules/d8.test.ts).
B25 | Drift engine | Auto-resolve pass + finding lifecycle (open/corrected/ignored/snoozed) | Rules §0 | P4 | M | B10 | Done | src/db/findings.ts persistFindings() -- already built (as part of B27's query-service work, untracked until now) and wired into src/cli/drift.ts. Inserts fresh findings as open (ON CONFLICT upsert on team_id+dedupe_key, one open row per key), flips any previously-open finding the current rule run no longer produces to corrected + resolved_at=now(). Verified live: ran drift (4 open incl. D1:NOVA-129), re-synced with ASOF_DEMO_PHASE=2 (PR #84 merged), re-ran drift -- D1:NOVA-129 flipped to corrected, detected_at preserved, resolved_at stamped, and the brief correctly rendered it under Since Yesterday / Resolved. NOT done: ignored/snoozed transitions -- those need a feedback action (B35), not built yet.
B26 | Drift engine | Per-team rule config API + defaults from onboarding workflow mapping | Config table | P4 | M | B25 | Not Started
B27 | Query service | Typed read functions: get_drift_findings, get_person_state, get_sprint_state, get_changes_since | §6 | P4 | M | B17 | Done | src/api/server.ts + routes/{today,standup}.ts (Fastify) -- GET /api/today, GET /api/standup, backed by db/repository.ts, db/findings.ts, and new db/personState.ts (per-person Shipped/In-flight/Flags, computed on the fly, no stored aggregate -- invariant #5). Verified live via curl and browser.
B28 | LLM layer | Chat Q&A: Claude tool-use over query service, SSE streaming, source-chip citations | FR-4 | P4 | L | B27 | Done | Tested live in the user's real Chrome (mic permission actually granted there, unlike the sandboxed dev browser). Found + fixed 2 real bugs via live testing: (1) React 18 StrictMode dev double-effect-invocation left a shared pausedRef stuck true after mount, silently disabling continuous mode's auto-restart -- looked like 'mic stops working'; fixed by resetting the ref explicitly on every mount. (2) Wake-word matching was exact-only and Chrome frequently mishears 'Jarvis' (an uncommon name) as Jervis/Charvis/Garvis/etc, so 'Hey Jarvis' would transcribe correctly but silently fail to match and do nothing; fixed with a Levenshtein-distance-2 fuzzy fallback plus visible 'Heard: ...' UI feedback so a miss is diagnosable instead of silent. Both fixes verified against the real running app (not a test double) by capturing the live onresult handler and dispatching synthetic Chrome SpeechRecognitionEvent objects through it -- confirmed full wake -> acknowledge -> question -> answer -> speak cycle end to end.
B29 | LLM layer | Brief generation job (daily 8:30 team-tz) + caching for cost ceiling | FR-5, NFR-4 | P4 | M | B13,B25 | Not Started
B30 | Slack | Slack app: post brief + High-severity flags; opt-in IC DMs with action buttons | FR-5, §9 | P4 | M | B29 | Not Started
B31 | Frontend | Today screen: live brief, risk cards, resolved ribbon | §9 IA-1 | P4 | M | B29 | Done | apps/web (Vite+React+TS+Tailwind, npm workspace) -- Today screen: sprint clock, ranked findings w/ severity border + clickable evidence chips, since-yesterday, latest narrated brief. Verified in browser (Claude Browser tool), 0 console errors, prod build clean.
B32 | Frontend | Standup screen: per-person Shipped/In-flight/Flags grid + Post to Slack | FR-6 | P4 | M | B27 | Done | apps/web Standup screen: per-person grid (Shipped/In flight/Flags), all items link to real Jira/GitHub source URLs. 'Post to Slack' NOT built (needs B30 Slack app, not started) -- button omitted rather than stubbed non-functional.
B33 | Frontend | Ask screen: streaming chat, source chips, suggested prompts | FR-4 | P4 | M | B28 | Not Started
B34 | Frontend | Settings: connections, user mapping, rule thresholds, transparency page, delete | FR-7, FR-8 | P4 | L | B26 | Not Started
B35 | Feedback | Correct/ignore/snooze actions + per-team suppression store | FR-7 | P4 | M | B25 | Done | POST /api/findings/:id/feedback (src/api/routes/feedback.ts, src/db/findings.ts recordFeedback). ignore -> finding.status='ignored' + permanent suppression row scoped to dedupe_key (persistFindings checks it before reopening). snooze -> snoozed_until=+3 days (migrations/002_feedback_lifecycle.sql), persistFindings reopens the same row in place once expired. correct -> logs feedback only, no status change. Frontend: FindingCard has Correct/Intentional-ignore/Snooze buttons; ignore/snooze remove the card live. Verified via curl and live in the running web app (ignored a card, watched it disappear, confirmed DB). Fixed a bug found along the way: drift.ts was printing raw rule output instead of the actual persisted-open findings, which silently diverged once suppression existed. NOT done: pattern-level suppression (only exact dedupe_key scope); suppression management UI (B34/Settings).
B36 | Testing | 32+ rule fixtures (TP, boundary, FP-trap, resolution per rule) in CI | Rules test gate | P4 | L | B24 | Done | 35 fixture tests across D1-D8 (test/rules/*.test.ts), exceeds the 32 minimum, each rule has TP/boundary/FP-trap/resolution. .github/workflows/ci.yml already runs npm test (+typecheck, +lint) on push/PR to main. Untracked until now -- exit criteria were already met as of B20-B24.
B37 | Infra | Fly.io/Railway deploy, Sentry, PostHog, secrets management | §6 | P4 | M | B1 | Not Started
B38 | Infra | Tenant purge job (<= 24h) + audit of read scopes | NFR-1 | P4 | M | B37 | Not Started
Backlog summary
P3 items done
P4 items done